ElectraHub Platform

REST to gRPC Migration Plan

API Gateway → Backend Microservices

March 27, 2026

Version 1.0

Status: Draft

# Table of Contents

(Update this field in Word: right-click → Update Field)

# 1. Executive Summary

This document outlines the migration plan to replace REST-based inter-service communication between the ElectraHub API Gateway and backend microservices with gRPC. The migration targets internal service-to-service calls only; the external-facing REST API exposed to frontend clients remains unchanged.

## 1.1 Current Architecture

The API Gateway (Spring Boot 4.0.1, Java 21) acts as a transparent reverse proxy, forwarding HTTP requests to 7 backend services via Spring’s RestClient. Routing is path-prefix-based and configured in application.yaml. The gateway also fetches RBAC policies from the user-service over REST on a 30-second polling interval.

## 1.2 Why gRPC?

Performance: Protobuf binary serialization is 5–10x smaller and 3–5x faster than JSON, reducing latency and CPU overhead on every proxied request.

Strongly-typed contracts: .proto files serve as a single source of truth, enabling compile-time validation and eliminating runtime deserialization surprises.

Streaming: gRPC’s bidirectional streaming is ideal for real-time features like RBAC policy push, charger status updates, and session meter values.

HTTP/2 multiplexing: Multiple in-flight RPCs share a single TCP connection, removing head-of-line blocking and reducing connection overhead to K8s services.

Code generation: Automatic client/server stubs in Java eliminate hand-written REST clients and DTOs.

## 1.3 Scope

| In Scope | Out of Scope |
| --- | --- |
| API Gateway → backend microservice calls (7 routes) | External client → API Gateway REST API |
| RBAC policy fetch (gateway → user-service) | Frontend applications (Angular, iOS) |
| Internal service-to-service contracts (.proto files) | OCPP WebSocket protocol (charger communication) |
| New shared proto module in Maven | OCPI roaming protocol endpoints |
| Health checks and observability over gRPC | Database schema or migration changes |

# 2. Current State Analysis

## 2.1 Service Inventory

All services in the ElectraHub platform share a uniform technology stack: Java 21, Spring Boot 4.0.1, Maven, PostgreSQL, Redis, and Micrometer/Prometheus observability. None currently have gRPC dependencies or .proto files.

| Service | Route Prefix | Port | Key Endpoints |
| --- | --- | --- | --- |
| auth-service | /auth | 8080 | Login, register, refresh, countries |
| user-service | /user | 8082 | User CRUD, admin, RBAC policy (internal) |
| subscription-service | /subscription | 8086 | Subscription audit, utilization |
| payment-service | /payment | 8083 | Wallet provisioning, top-up, auto top-up |
| charger-mgmt-service | /charger, /charger-mgmt | 8086 | Charger CRUD, admin operations |
| pricing-service | /pricing | 8092 | Price signals, OCPI tariffs, search, calculate |
| web-socket-connector | /ws | 8091 | WebSocket relay for OCPP |

## 2.2 Communication Patterns

The gateway uses two distinct REST communication patterns:

### 2.2.1 Transparent Proxy (GatewayProxyController)

The GatewayProxyController catches all requests via @RequestMapping("/"), extracts the first path segment as a service prefix, resolves the backend URL from RouteRegistry, and forwards the full HTTP request (method, headers, query string, body) using RestClient. Response bytes are returned as-is. This is the primary traffic path for all 7 backend services.

### 2.2.2 Typed REST Call (RBAC Policy Fetch)

The CachedRbacPolicySnapshotProvider makes a typed GET request to user-service’s internal RBAC endpoint every 30 seconds, deserializing the JSON response into RemoteRbacPolicyResponse DTOs. This is a structured, internal-only API that is ideal for early gRPC migration.

## 2.3 Key Observations

No existing gRPC infrastructure: None of the 11 services have proto files, gRPC dependencies, or gRPC server/client configurations.

Uniform tech stack: All services use Spring Boot 4.0.1 + Java 21, making a standardized gRPC integration approach feasible.

Simple routing: The gateway’s transparent proxy pattern means most logic is request forwarding — the migration primarily changes the transport layer, not business logic.

Kubernetes-native discovery: Services use K8s DNS names (e.g., auth-service:8080), which maps directly to gRPC channel targets.

WebSocket connector should remain REST/WS: The web-socket-connector relays OCPP WebSocket connections and is not suitable for gRPC replacement.

# 3. Target Architecture

## 3.1 High-Level Design

In the target state, the API Gateway will continue to accept REST requests from external clients (frontends, mobile apps) but will forward them to backend services over gRPC instead of REST. Each backend service will expose a gRPC server alongside its existing REST controllers during the dual-stack period. The external REST API surface remains identical.

## 3.2 Architectural Decisions

| Decision | Choice | Rationale |
| --- | --- | --- |
| Proto management | Shared Maven module (electrahub-proto) | Single source of truth, versioned with platform, compile-time safety |
| gRPC framework | grpc-spring-boot-starter (grpc-ecosystem) | Mature Spring Boot integration, auto-config, interceptor support |
| Serialization | Protocol Buffers v3 | Industry standard, backward-compatible evolution, compact binary |
| Service discovery | Kubernetes DNS (unchanged) | gRPC channels target K8s service names directly |
| Dual-stack period | REST + gRPC in parallel | Zero-downtime migration; roll back by switching to REST clients |
| WebSocket connector | Remains REST/WebSocket | OCPP protocol requires WebSocket; gRPC not applicable |
| Error handling | gRPC Status codes + metadata | Map to HTTP status codes at gateway for client compatibility |
| Deadline propagation | gRPC deadlines from gateway | Replace HTTP timeouts with gRPC deadline propagation |

## 3.3 Module Structure

A new shared Maven module electrahub-proto will house all .proto files and generate Java stubs at build time. Every service that participates in gRPC will depend on this module.

| Module/Artifact | Contents | Consumed By |
| --- | --- | --- |
| electrahub-proto | .proto files, generated Java stubs (messages + gRPC services) | All services |
| api-gateway | gRPC channel config, stub beans, gateway-side interceptors | N/A (top-level consumer) |
| Each backend service | gRPC server implementation classes, server interceptors | api-gateway (via gRPC) |

## 3.4 Proto File Organization

Proto files will be organized by domain, mirroring the service boundaries:

| Proto File | Package | Service Definition |
| --- | --- | --- |
| auth.proto | electrahub.auth.v1 | AuthService (login, register, refresh, countries) |
| user.proto | electrahub.user.v1 | UserService (CRUD, admin), RbacService (policy) |
| subscription.proto | electrahub.subscription.v1 | SubscriptionService (audit, utilization) |
| payment.proto | electrahub.payment.v1 | PaymentService (wallet, top-up, auto top-up) |
| charger.proto | electrahub.charger.v1 | ChargerService (CRUD, admin) |
| pricing.proto | electrahub.pricing.v1 | PricingService (signals, tariffs, search, calculate) |
| common.proto | electrahub.common.v1 | Shared messages (Pagination, ErrorDetail, etc.) |

# 4. Migration Phases

The migration follows a phased approach to minimize risk and allow validation at each step. Each phase is independently deployable and rollback-safe.

## Phase 0: Foundation (Week 1–2)

Set up the shared proto infrastructure and tooling before touching any service.

### 4.1.1 Create electrahub-proto Maven Module

Create a new top-level Maven module electrahub-proto alongside existing services.

Configure protobuf-maven-plugin with os-maven-plugin for cross-platform protoc resolution.

Configure grpc-java code generation plugin to produce service stubs.

Add the module to the parent POM or CI pipeline so it builds first.

### 4.1.2 Define Common Protos

Create common.proto with shared message types: Pagination, SortOrder, ErrorDetail, Empty wrappers.

Establish proto style guide: package naming (electrahub.{domain}.v1), field naming (snake_case), versioning strategy.

Set up buf lint or protolock for schema validation and backward-compatibility checks in CI.

### 4.1.3 Add gRPC Dependencies to API Gateway

Add grpc-client-spring-boot-starter (net.devh) to the gateway’s pom.xml.

Add electrahub-proto as a dependency.

Configure gRPC channel beans in application.yaml with K8s DNS targets.

Add gRPC health check and metrics interceptors (Micrometer integration).

Deliverables: Buildable proto module, CI pipeline generating Java stubs, gateway compiles with gRPC client dependencies.

## Phase 1: Pilot — RBAC Policy over gRPC (Week 3–4)

Migrate the simplest, most isolated internal call first: the RBAC policy fetch from gateway to user-service. This is a single typed endpoint with no external client exposure, making it the ideal pilot.

### 4.2.1 Define rbac.proto

Define RbacService with a unary RPC: GetPolicy(GetPolicyRequest) returns (RbacPolicyResponse).

Model the response to match the existing RemoteRbacPolicyResponse DTO structure.

Consider adding a server-streaming variant StreamPolicy for real-time push (replacing 30s polling).

### 4.2.2 Implement gRPC Server in user-service

Add grpc-server-spring-boot-starter dependency to user-service’s pom.xml.

Create RbacGrpcService class annotated with @GrpcService, implementing the generated RbacServiceGrpc.RbacServiceImplBase.

Wire existing RBAC repository/service logic into the gRPC handler.

Configure gRPC server port (e.g., 9082) in application.yaml alongside existing REST port 8082.

Add gRPC health service (grpc-health-probe) for K8s readiness checks.

### 4.2.3 Update Gateway RBAC Client

Create a new GrpcRbacPolicySnapshotProvider implementing the existing RbacPolicySnapshotProvider interface.

Inject the auto-configured RbacServiceBlockingStub (or async stub for streaming).

Use a feature flag (e.g., app.rbac.transport=grpc|rest) to toggle between implementations.

If using streaming: replace 30s scheduled polling with a long-lived server-stream subscription with automatic reconnection.

### 4.2.4 Validate and Observe

Deploy to dev/staging with the feature flag set to grpc.

Compare RBAC policy fetch latency, payload size, and error rates against REST baseline.

Validate fallback: flip feature flag to rest and confirm seamless rollback.

Deliverables: RBAC policy fetched over gRPC, streaming option evaluated, feature-flag-controlled rollback, latency/size benchmarks.

## Phase 2: First Proxied Service — auth-service (Week 5–7)

Migrate the first externally-proxied service to validate the full request/response forwarding pattern over gRPC. The auth-service is chosen because it has a small, well-defined API surface (login, register, refresh, countries) and is critical enough to prove the pattern under real load.

### 4.3.1 Define auth.proto

Define AuthService with RPCs: Login, Register, RefreshToken, ListCountries.

Model request/response messages to match existing REST DTOs (AuthRequest, AuthResponse, CountryDto, etc.).

Include standard metadata fields for request-id, trace-id propagation.

### 4.3.2 Implement gRPC Server in auth-service

Add grpc-server-spring-boot-starter dependency.

Create AuthGrpcService implementing AuthServiceGrpc.AuthServiceImplBase.

Delegate to existing Spring service layer (no business logic duplication).

Map Spring Security exceptions to appropriate gRPC Status codes (UNAUTHENTICATED, PERMISSION_DENIED, etc.).

### 4.3.3 Replace Gateway Proxy for /auth Routes

Create a dedicated AuthGrpcForwarder component in the gateway.

Intercept /auth/ requests in the gateway before they reach the generic GatewayProxyController.

Convert the incoming HttpServletRequest to the appropriate protobuf request message.

Call the gRPC stub and convert the protobuf response back to JSON (for the external REST client).

Preserve all existing HTTP status codes, headers, and error response formats.

Use a feature flag to route /auth traffic to either the gRPC forwarder or the legacy REST proxy.

### 4.3.4 Gateway Request Translation Layer

A key architectural component is the GrpcRequestTranslator pattern. Since external clients send JSON over REST and backend services will speak protobuf over gRPC, the gateway needs a translation layer:

Inbound: Parse JSON request body → build protobuf request message

Outbound: Serialize protobuf response → JSON response body

Error mapping: gRPC Status → HTTP status code (e.g., NOT_FOUND → 404, INVALID_ARGUMENT → 400)

Header propagation: Copy relevant HTTP headers into gRPC metadata (Authorization, X-Request-Id, etc.)

Deliverables: Auth-service fully reachable over gRPC from gateway, JSON translation layer proven, error mapping validated, feature-flag rollback tested.

## Phase 3: Remaining Services (Week 8–14)

With the translation pattern validated on auth-service, roll out gRPC servers to the remaining services in priority order. Each service follows the same pattern established in Phase 2.

| Priority | Service | Week | Rationale |
| --- | --- | --- | --- |
| 1 | user-service | 8–9 | Already has gRPC server (RBAC); extend to full User API |
| 2 | payment-service | 9–10 | Critical path for charging sessions. Benefits from lower latency |
| 3 | subscription-service | 10–11 | Moderate complexity, moderate traffic. Good for parallel work |
| 4 | charger-mgmt-service | 11–12 | Dual route prefixes need careful handling |
| 5 | pricing-service | 12–13 | Complex query patterns. Validates gRPC with rich request models |
| 6 | web-socket-connector | 14 (opt) | Evaluate gRPC streaming as alternative. May remain REST |

For each service, the steps are: (1) define .proto, (2) implement gRPC server, (3) create gateway forwarder, (4) feature-flag deploy, (5) validate and promote.

## Phase 4: Decommission REST Internals (Week 15–18)

Once all services are stable on gRPC with feature flags set to gRPC in production:

Remove REST controllers that were only used for internal gateway traffic (keep external-facing ones if any exist).

Remove the generic GatewayProxyController transparent proxy (replaced by service-specific gRPC forwarders).

Remove RestClient and HttpClientConfig from the gateway.

Remove feature flags and dual-stack configuration.

Update Swagger/OpenAPI documentation to reflect internal APIs are now gRPC (external API docs remain REST).

Archive REST integration tests; ensure gRPC integration tests provide equivalent coverage.

# 5. Technical Implementation Details

## 5.1 Maven Dependencies

The following dependencies are needed across the platform:

| Artifact | Where | Purpose |
| --- | --- | --- |
| io.grpc:grpc-netty-shaded | All services | gRPC transport (Netty-based, shaded to avoid conflicts) |
| io.grpc:grpc-protobuf | Via electrahub-proto | Protobuf serialization for gRPC |
| io.grpc:grpc-stub | Via electrahub-proto | Generated stub base classes |
| net.devh:grpc-server-spring-boot-starter | Backend services | Auto-configures gRPC server with Spring Boot |
| net.devh:grpc-client-spring-boot-starter | api-gateway | Auto-configures gRPC channels and stubs |
| io.grpc:grpc-services | All services | Health check and reflection services |

## 5.2 gRPC Channel Configuration (Gateway)

The gateway’s application.yaml will define gRPC channels for each backend service, replacing the current REST route registry:

| Current REST Config | New gRPC Config |
| --- | --- |
| gateway.routes.auth: http://auth-service:8080 | grpc.client.auth-service.address: dns:///auth-service:9080 |
| gateway.routes.user: http://user-service:8082 | grpc.client.user-service.address: dns:///user-service:9082 |
| gateway.routes.payment: http://payment-service:8083 | grpc.client.payment-service.address: dns:///payment-service:9083 |
| gateway.routes.subscription: http://subscription-service:8086 | grpc.client.subscription-service.address: dns:///subscription-service:9086 |
| gateway.routes.charger: http://charger-mgmt-service:8086 | grpc.client.charger-service.address: dns:///charger-mgmt-service:9086 |
| gateway.routes.pricing: http://pricing-service:8092 | grpc.client.pricing-service.address: dns:///pricing-service:9092 |

## 5.3 Error Code Mapping

The gateway’s translation layer must map gRPC status codes back to HTTP for external clients:

| gRPC Status | HTTP Status | Use Case |
| --- | --- | --- |
| OK | 200 | Successful response |
| INVALID_ARGUMENT | 400 | Validation errors, malformed requests |
| UNAUTHENTICATED | 401 | Missing or invalid JWT |
| PERMISSION_DENIED | 403 | RBAC authorization failure |
| NOT_FOUND | 404 | Resource not found |
| ALREADY_EXISTS | 409 | Duplicate registration, conflict |
| RESOURCE_EXHAUSTED | 429 | Rate limiting |
| INTERNAL | 500 | Unexpected server errors |
| UNAVAILABLE | 503 | Service temporarily unavailable |
| DEADLINE_EXCEEDED | 504 | Request timeout |

## 5.4 Observability

Metrics: grpc-spring-boot-starter auto-registers Micrometer metrics (grpc.server.*, grpc.client.*) for request count, latency histograms, and status code distribution. These feed into existing Prometheus/Grafana dashboards.

Tracing: Propagate trace context (W3C Trace Context or B3) via gRPC metadata using interceptors. Integrate with existing distributed tracing.

Health checks: Each gRPC server registers a standard gRPC health service. K8s probes use grpc-health-probe binary or Spring Boot Actuator health indicators.

Logging: gRPC interceptors log method name, duration, and status code at DEBUG level, matching the existing ObservabilityAspect pattern.

## 5.5 Kubernetes Changes

Add a new container port (e.g., 9080) for gRPC in each Deployment spec.

Create new K8s Services or add a named port (grpc) to existing Services targeting the gRPC port.

Update liveness/readiness probes to include gRPC health checks.

No changes to Ingress/external load balancers (external traffic remains REST via the gateway).

# 6. Risk Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Proto schema evolution breaks clients | High | Use buf breaking-change checks in CI. Follow proto3 backward-compatible evolution rules. |
| gRPC adds complexity to debugging | Medium | Enable gRPC reflection service in dev/staging for grpcurl. Add structured logging interceptors. |
| Performance regression during dual-stack | Medium | Load test both stacks before cutover. Feature flags allow instant rollback to REST. |
| Team unfamiliarity with gRPC/protobuf | Medium | Conduct half-day workshop in Week 1. Pilot (Phase 1) is intentionally small for learning. |
| JSON-to-protobuf translation overhead | Low | Benchmark translation layer. JsonFormat (protobuf-java-util) is optimized. |
| K8s service mesh gRPC support gaps | Low | Modern service meshes fully support gRPC/HTTP2. Verify mTLS and load balancing. |
| WebSocket connector migration complexity | Low | Explicitly out of scope for initial rollout. Evaluate in Phase 3 only if beneficial. |

# 7. Testing Strategy

## 7.1 Unit Tests

Test each gRPC service implementation using grpc-testing (InProcessServer) for fast, in-memory gRPC calls.

Test proto message serialization/deserialization round-trips.

Test gateway translation layer: JSON → protobuf → JSON with edge cases (null fields, large payloads, unicode).

## 7.2 Integration Tests

Use @SpringBootTest with embedded gRPC server to test full request flow.

Verify error mapping: trigger each gRPC status code and validate the corresponding HTTP response.

Test feature flag toggling: switch between REST and gRPC mid-test and verify identical behavior.

## 7.3 Contract Tests

Use buf breaking in CI to catch backward-incompatible proto changes.

Validate generated stubs match deployed service implementations via reflection.

## 7.4 Performance Tests

Extend existing JMeter regression suite (jmeter-regression) to measure latency delta post-migration.

Benchmark: REST proxy vs. gRPC forwarder for identical request/response patterns.

Load test gRPC channel connection pooling under concurrent requests.

# 8. Timeline Summary

| Phase | Duration | Milestone |
| --- | --- | --- |
| Phase 0: Foundation | Week 1–2 | Proto module builds, gateway compiles with gRPC client deps |
| Phase 1: Pilot (RBAC) | Week 3–4 | RBAC policy fetch over gRPC in staging, streaming evaluated |
| Phase 2: auth-service | Week 5–7 | First full proxied service on gRPC, translation layer proven |
| Phase 3: Remaining services | Week 8–14 | All 6 services running gRPC in production |
| Phase 4: Decommission REST | Week 15–18 | Internal REST removed, single gRPC transport path |

Total estimated duration: 18 weeks (4.5 months) from kickoff to full decommission of internal REST. The dual-stack period (Weeks 3–14) ensures zero-downtime and safe rollback at every stage.

# 9. Success Criteria

All internal gateway-to-service traffic routed over gRPC (excluding WebSocket connector).

External REST API responses are byte-identical (status codes, JSON structure, headers) before and after migration.

P99 latency for proxied requests reduced by at least 20% compared to REST baseline.

Zero production incidents caused by the migration.

All services pass existing JMeter regression suite without test modifications.

Feature-flag rollback tested and documented for each service.

Proto backward-compatibility checks running in CI for every pull request.

# 10. Appendix

## 10.1 Sample Proto Definition (RBAC)

Below is an illustrative proto definition for the RBAC policy service, demonstrating the target contract style:

syntax = "proto3";

package electrahub.user.v1;

service RbacService {

rpc GetPolicy(GetPolicyRequest) returns (RbacPolicyResponse);

rpc StreamPolicy(StreamPolicyRequest) returns (stream RbacPolicyResponse);

}

message GetPolicyRequest {

string api_key = 1;

}

message StreamPolicyRequest {

string api_key = 1;

}

message RbacPolicyResponse {

string version = 1;

string role_hierarchy = 2;

string default_decision = 3;

repeated RbacRule rules = 4;

}

message RbacRule {

string name = 1;

repeated string methods = 2;

string path_pattern = 3;

string effect = 4;

bool allow_anonymous = 5;

repeated string required_roles = 6;

}

## 10.2 gRPC Status Code Quick Reference

Complete mapping used by the gateway translation layer for converting gRPC errors to HTTP responses. The gateway should include gRPC error details (via Status.getDescription() and rich error model trailers) in the JSON response body for debugging purposes.